## Team A
Product Backlog Team A (Venkata, Meet)
|  |  | Venkata Meet | low / medium / high | To Do – planned for this sprint, not started In Progress – someone is actively working on it In Review / Testing – code/design is done, needs review or test Done – accepted by the team / PO, meets Definition of Done
Sprint No./Task No | Task Name | User Story | Assigned to | Priority | Status | Start Date | Finish Date | Assigned to Sprint …
1 | Antigravity installation and set up | As a Developer I want to have Antigravity installed and set up. | Venkata | high | In Progress | 10. Feb.
1.1 | GitHub setup | As a Developer I want to have a GitHub Respository
1.2 | GitHub connected to my Antigravity | As a Developer I want to have the GitHub Respository connected to my IDE (Antigravity)
1.3 | Basic Workflow test | As a Product Owner I want to make sure that the workflow between local IDEs and GitHub is working. Therefore we need to run a short test: 1) Instruct Antigravity to build a tiny web-based application 'hello-counter' (Button pressed --> add 1 to the counter). Test. 2) Commit to GitHub. 3) Add functionality: Add a seconds button decreasing the counter. 4) Commit added funtionality 5) Roll back. |  |  |  | 11.Feb.
| example | As persona Lisa Becker I want to see metric x with the possibility of filtering by LOR level BZ + BZR + PLR | Venkata + Meet | medium |  | not yet started

## Team B
Product Backlog Team A (Venkata, Meet)
|  |  | Vinay Sainath | low / medium / high | To Do – planned for this sprint, not started In Progress – someone is actively working on it In Review / Testing – code/design is done, needs review or test Done – accepted by the team / PO, meets Definition of Done
Sprint No./Task No | Task Name | User Story | Assigned to | Priority | Status | Start Date | Finish Date | Assigned to Sprint …
1 | Antigravity installation and set up | As a Developer I want to have Antigravity installed and set up. | Venkata | high | In Progress | 10. Feb.
1.1 | GitHub setup | As a Developer I want to have a GitHub Respository
1.2 | GitHub connected to my Antigravity | As a Developer I want to have the GitHub Respository connected to my IDE (Antigravity)
1.3 | Basic Workflow test | As a Product Owner I want to make sure that the workflow between local IDEs and GitHub is working. Therefore we need to run a short test: 1) Instruct Antigravity to build a tiny web-based application 'hello-counter' (Button pressed --> add 1 to the counter). Test. 2) Commit to GitHub. 3) Add functionality: Add a seconds button decreasing the counter. 4) Commit added funtionality 5) Roll back. |  |  |  | 11. Feb.
| example | As persona Lisa Becker I want to see metric x with the possibility of filtering by LOR level BZ + BZR + PLR | Venkata + Meet | medium |  | not yet started

## Statuses for Sprint Tasks
To Do – planned for this sprint, not started
In Progress – someone is actively working on it
In Review / Testing – code/design is done, needs review or test
Done – accepted by the team / PO, meets Definition of Done